## Slide 1: Progress on Implementation of 2023 undertakings
Dr. Wakooba Peter
November 13, 2024

## Slide 2: HIV Prevention (1)
Undertaking | Activity | Progress | Score
Primary Prevention | Scale up the “expanded Time Up” campaign | Refined SBCC campaign that includes NCD, new PrEP options and condom programming for young people rolled out. | 
PMTCT | Scale up the Global Alliance (GA)/Accelerating Progress in Paediatric and PMTCT (AP3) Activities to fidelity. | HIV re-testing Improved from 36% to 62% | 
 |  | Capacity building for the HWs in the MNH platform for HIV re-testing conducted | 
 |  | Task shifting to peer mothers under AP3. ongoing | 
 |  | Male involvement. | 
 |  | Scaled up elimination of and syphilis HEP B and other STIs. challenge is stock out of duo test kits | 

## Slide 3: HIV Prevention (2)
Undertaking | Activity | Progress | Score
AGYW | Strengthen the Multisectoral response at subnational level | Harmonized Multi-sectoral M&E framework and reporting tools for the AGYW have been developed in final stages of approval | 
 | Guidelines, tools, and packages | Standardize the risk and vulnerability assessment tool developed, being rolled out by TASO in GF supported districts. | 
 |  | Developed peer strategy which awaits approval and dissemination | 
 |  | Development of HIV prevention package for the Adolescent boys and young men was completed, awaiting approval and dissemination | 

## Slide 4: HIV Prevention (3)
Undertaking | Activity | Progress | Score
HTS | Optimize HTS integration | In March the 2024 CAST campaign integrated HIV and Malaria | 
 |  | Roll out HTS Optimization guidelines is ongoing to improve efficiency and mitigate stock out of test kits. | 
PrEP Programming | Optimize the new PrEP technologies among KP and PP where epidemic is concentrated | MOH – developed data security and safety guidelines, the toll out is ongoing Dissemination of the PrEP guidelines including popularisation of available options | 
Condom Programming | Roll out a condom tracking system | Condom distribution and tracking systems was developed and awaits clearance | 
KP | Disseminate findings of the Legal Environmental Assessment | Only done at national | 

## Slide 5: Care and Treatment
Undertaking | Activity | progress | Score
DSD models | Refine DSDM models optimizing community human resource. | Roll out of community model is ongoing | 
 | Conduct Evaluation of DSD (YAPS, Integrated community, G-ANC/PNC, HIV&NCD integration. | Data collection completed for GANC/PNC and NCD evaluations. (June 2024) | 
Notes: In HIV Care and Treatment was noted on the key undertakings –
For data management and use - the roll out of EMRs is improving use of the CQI audit tool and Case Based Suveillance - currently over 600 facilities were active as of June 2024.
Differentiated service delivery models continue to evolve and are rolled out.
For the program evaluations of focus, data collection was completed and plans for dissemination of findings are ongoing

## Slide 6: Social Support & Social Protection (1)
Undertaking | Activity | progress | Score
Stigma and discrimination reduction | Dissemination of the National Policy Guidelines for Ending Stigma and Discrimination across all levels. | Anti-Stigma Policy Guidelines disseminated and implemented | 
 | Complete the Stigma Index Study | Stigma study completed and disseminated | 
 | Invest in media relations to create favourable conditions for increased strategic reporting on HIV related cases | Media engagements held to orient media houses on strategic reporting on stigma and discrimination | 
Notes: All the commitements that were agreed upon were accomplished

## Slide 7: Social Support & Social Protection (2)
Undertaking | Activity | Progress | Score
Socio-economic strengthening | Scale up comprehensive AGYW socioeconomic intervention to 18 high incidence districts. | Vulnerable AGYW reached. MOGLSD is rolling out joint program on adolescents and Teenage Pregnancy in 24 districts | 
 | Continue with household economic recovery programs targeting households whose livelihoods were severely affected by the COVID-19 pandemic and the associated measures and integration into the PDM. | Resources for ongoing programmes sustained and programmes integrated into PDM | 

## Slide 8: Social Support and Social Protection (3)
Undertaking | Activity | Progress | Score
Gender-Based Violence | Expand availability of psycho-social support to GBV survivors. | Psycho-social support Done in refugee settlement with support of UNHCR. | 
 | Train PLHIV, KPs, vulnerable groups, law enforcement officers and communities on rights awareness and legal literacy to facilitate early reporting of GBV incidents. | MoGLSD, PLHIV Networks, PLHIV-led CSOs, Human Rights CSOs Training ongoing | 
 | Conduct a bottleneck analysis on GBV/VAC cascade from event to conviction of perpetuators. | Multi sectoral engagement (MoH, MoGLSD, MoJCA) is not yet done | 
Child Protection& Violence against Children | Harmonise monitoring mechanisms for GBV/VAC | Conducted engagements with stakeholders; working on revision of the GBV policy; Steering committee in place. | 

## Slide 9: System Strengthening (1)
Undertaking | Activity | Progress | Score
Governance and Leadership | Disseminate findings of national stigma survey | Disseminate findings of the National stigma Index Survey conducted by MakSPH (MOH, CSOs. | 
 | Capacity Building of the RRH | Capacity building for RRHs in line with the Regional Strategy. | 
 |  | Conduct annual RRH capacity assessment. | 
Financing | Ensuring sustainability of the response | Developed the Resource mobilization strategy | 
 |  | NASA for 2021/22 completed & report finalised. | 
 |  | Development of the sustainability Roadmap for HIV response is ongoing | 

## Slide 10: System Strengthening (2)
Undertaking | Activities | Progress | Score
Strengthen M&E systems | Roll out the updated HMIS tools for general and key populations | National TOT conducted. Awaiting printing of tools. | 
 | Roll out the national GBV database to harmonize reporting across sectors | Only 54/135 districts reporting. due to multiple challenges. | 
 | Advocacy for unique client identification system across sectors to improve data quality (UAC) | No progress | 
 | Operationalize EMIS and start reporting on HIV indicators under the education sector | System is operational. | 
 | Finalise the development of the national HIV and AIDS research agenda | Finalized and disseminated | 

## Slide 11: Undertakings for implementation for FY2024/2025

## Slide 12: HIV Prevention
Undertaking | Activity | Lead Agency
AGYW | Widely disseminate at sub national all newly developed policies and guidelines on AGYW programming The multisectoral accountability Framework for ending HIV among AYP by 2030 Risk and vulnerability assessment tool - MOH Peer implementation strategy - MOH | UAC, MoH & IPs
 | Disseminate the revised minimum package for the AGYW | 
 | Conduct mentorships to the districts on AGYW service delivery to improve the capacity of the HWs to provide youth friendly services | 
 | Advocate for inclusion of AGYW in HIV/AIDS TWG at the district | 
 | Support districts to set targets for the AGYW | 
PrEP | Revision of the PrEP technical guidelines and training materials | MoH, CSOs
 | Pilot Pharmacy refill model for distribution of PrEP supplies | MOH

## Slide 13: Care and Treatment
Undertaking | Activity | Lead Agency
DSD | Roll out integrated community DSD models | MOH
TB/HIV | Disseminate TB-DSD guidelines | MOH -NTLP
 | Development of guidance on TB integration into the community pharmacy | MOH -NTLP
 | TB Integration into electronic Medical Records (EMR) | MOH -NTLP
 | Roll out TB/HIV M&E Mortality Surveillance Framework: | MOH -NTLP
ART | Adopt unique client identification for effective retention monitoring, performance monitoring | MOH-DHI
Care | Finalize program evaluations and disseminate findings | MOH

## Slide 14: Social Support and Social Protection
Undertaking | Activity | Lead Agency
Policy guidance | Disseminate the Parenting guidelines Integrate Parenting guidelines in the school activities (PTA, Clubs etc.) | MGLSD, UAC , MOES
 | Fast track the revision and dissemination of the GBV policy to align it with current priorities and indentified gaps/barriers | MOGLSD
 | Roll out school -health facility guidelines | MOES, MOH
 | Disseminate the Stigma and Discrimination policy that was translated into sign language | CSO, MOH, MOGLSD
GBV programming | Expand the Survivors Shelters to other districts in need | MoGLSD
 | MGLSD to continue to Roll out the national GBV database to harmonize reporting across sectors - beyond the 54/135 districts currently using it | MOGLSD

## Slide 15: System Strengthening
Undertaking | Activity | Lead Agency
Strengthen the Multisectoral coordination | Fast track the completion and dissemination of the HIV Coordination guidelines for the functionality of the sub national coordination structures (DACS, SACs, etc) | UAC
 | Strengthen the HIV mainstreaming guidelines | 
 | For infrastructure engage NITA-U, Energy Ministry, and Health in digitalization planning | UAC, MOH
 | Functionalize the online accreditation process for NGOs,CSOs accreditation and complete accreditation | UAC

## Slide 16: System Strengthening
Undertaking | Activity | Lead Agency
Financing | Fast track the Institutionalization of NASA reporting | UAC
 | Finalize development of the HIV Sustainability framework and roadmap | UAC
Human resources | Understaffing only 33% of staffing position filled according to the new staffing structure | MoFPED, MOH, MOLG, MOES
Community systems strengthening | Expand CHEWs training to more districts as guided by the National community health strategy anchored on the Primary Health Care (PHC) systems to quicken the achievement of Universal Health Coverage (UHC). Only 4 districts had stated training of CHEWs | MoH

## Slide 17: System Strengthening
Undertaking | Activity | Lead Agency
M&E and research | Finalize roll out of revised HMIS tools | MOH
 | Conduct audits/studies/ reviews/evaluation to update knowledge of drivers of the epidemic and barriers to services access | UAC, MOH, MoGLSD, MoES
 | Disseminate completed surveys e.g., UPHIA 2020/21 | MOH
 | Conduct UPHIA 2024/25 | MOH
 | Conduct KP Stigma and Distrimination Survey | MOH, MoGLSD
 | Finalise and disseminate the ongoing surveys, surveillance, and program evaluations programs (YAPS, G-ANC, NCD etc) | MOH